## Sheet1
| Activities | Priority* | Starting period |  |  |  |  | Beneficiaries | Leading institutions | Implementing partners | Implementation progress | Implementation progress rate | Comments
|  |  | 2018 | 2019 | 2020 | 2021 | 2022 |  |  |  | Implementation progress
1 | 1. Strengthen sector coordination and regulations
Operational objective 1.1 | Operational objective 1.1 Increase sector coordination and synergies
1.1.1 | 1.1.1 Create an ICT sector core team to oversee roadmap design and implementation The core team plays a leading role to ensure a favourable expansion of youth economic opportunities in ICT through the monitoring of the roadmap implementation. The core team can be used as a stepping stone toward the creation of the ICT board. | ST | X | X | X |  |  | Sector stakeholders | ITAG | YEP |  |  |  | Completed | 0.25
1.1.2 | 1.1.2 Create an ICT board to oversee sector development, need of policy changes and investment in ICT infrastructure and to foster clustering culture Promote strategic clustering or consortium approaches in areas and situations where companies can complement (not compete against) each other in offering and providing solutions to clients, such as for public tender. | ST | X | X | X |  |  | Sector stakeholders | MOICI | PURA |  |  |  | Under completion | 0.5
1.1.3 | 1.1.3 Strengthen the capacities of the ICT sector association - To support the development of the sector - To advocate for policy changes - To actively participate in the design of curriculum in TVET - To promote ICT services by developing a national portal and organizing a demo day - To develop a code of conduct on quality and reliability of services. | ST | X | x |  |  |  | ITAG | MOICI | ITAG members |  |  |  | To be programmed | 0.75
1.1.4 | 1.1.4 Develop an official Yellow Pages for all ICT providers and reference mechanism The objective is to improve statistical data collection on ICT companies in order to develop an effective regulation, based on empirical needs. The data will also be used as a benchmark to evaluate the impact of the new regulations. | ST | X | X |  |  |  | Sector stakeholders | ITAG | ITAG YEP |  |  |  |  | 1
Operational objective 1.2 | Operational objective 1.2 Align regulations with sector’s development needs to stimulate ICT sector’s growth
1.2.1 | 1.2.1 Conduct a gap analysis of digital legislation (i.e. digital signatures, data protection and online payments, etc.), taking into account existing draft legislation to identify areas where improvements can be made. | ST | X | X | X |  |  | ICT stakeholders Consumers Bank | MOICI | Specialized foreign agency Central Bank
1.2.2 | 1.2.2 Finalize the regulations to foster the development of mobile banking and mobile moneyBased on identified gaps in digital legislation: (1) elaborate specific policy recommendations, including legislative text, to align digital legislation with the ICT sector’s long-term requirements (and the overall digital economy), and (2) develop related policy paper to form the basis of an advocacy and awareness-raising campaign. Establish a payment gateway, which is a crucial piece of infrastructure to enable government e-services and e-commerce applications. | ST | X | X |  |  |  | ICT stakeholders Consumers Bank | MOICI | PURA
1.2.3 | 1.2.3 Strengthen the ICT consumer protection law on mobile data Develop a legal obligation for telecom companies to report accurate mobile data usage. Negotiate the reduction of mobile data price to end users. | MT | x | X | X |  |  | ICT stakeholders Consumers Bank | MOICI | PURA
1.2.4 | 1.2.4 Assess the feasibility of establishing a tax on telecom companies to support the development of the ICT sector and access in remote rural areas Assess the feasibility of developing a tax and funding mechanism to collect contributions from telecom operators to subsidise the expansion of ICT in underserved communities, especially remote rural areas. | LT |  |  | X | X | X | MSMES in ICT-related services | MOICI | PURA Telecom companies
1.2.5 | 1.2.5 Design an e-governance plan and national open data initiativeWith the support of the ICT board, establish a working group to design an e-governance roadmap focusing on required policy, regulations changes and national open data initiative. | LT |  |  |  | X | X | ICT stakeholders | MOICI | PURA
Operational objective 1.3 | Operational objective 1.3 Create an enabling environment for fostering quality compliance and IP creation
1.3.1 | 1.3.1 Improve awareness and compliance with international quality standards through accreditation Develop and implement standardization and certification for methodologies, processes and products in order to increase the level of trust in the Gambian ICT product offering. Increase awareness of the public and private sector about ICT accreditations provided by international companies such as Microsoft, IBM, Oracle or Cisco. | ST | X | X | X |  |  | ICT stakeholders | PURA | ITAG TGSB
1.3.2 | 1.3.2 Assess existing intellectual property (IP) laws and agreements Review existence of prior analyses of WTO-TRIPs-aligned laws legislation on industrial property, copyright and related rights. | MT |  |  | X | X |  | ICT stakeholders Creative industries | MOICI | Specialized foreign agency
1.3.3 | 1.3.3 Build awareness of ICT companies toward IP registration and protection Improve private sector awareness about intellectual property registration and provide guidance regarding IP creation, application filing and registration. Review and improve existing processes to develop a new fast track IP registration by national IP offices. | MT |  |  | X | X | X | MSMES in ICT-related services | PURA NCAC for copyrights | PURA
2. | 2. Improve the quality and relevance of ICT skills development programmes
Operational objective 2.1 | Operational objective 2.1 Improve the coordination mechanism for the development of quality training in ICT
2.1.1 | 2.1.1 Support the development of inter-ministerial coordination arrangements for skills development in ICT Establish a working group composed of public, private and TVET through the ICT board. | ST | X |  |  |  |  | Value chain stakeholdersTVET | MOICI MOTIE | MoHER ST MOYS NAQAA NYC GIEPA GCCI Sector associations
2.1.2 | 2.1.2 Establish an ICT education providers’ working group The group will have the responsibility of promoting national development of skill standards, common curriculum, learning materials and teacher training programmes with the involvement of all TVET providers and industry. | ST | X |  |  |  |  | Value chain stakeholdersTVET | NAQAA | TVET providers
2.1.3 | 2.1.3 Update in the Gambia Skills Qualifications Framework (GSQF) for ICT and develop a quality insurance mechanism to certify training providers and their courses | ST | X | X |  |  |  | TVET providers | NAQAA | TVET providers
2.1.4 | 2.1.4 Integrate tracer studies mechanism in TVET management Train TVET management to carry out tracer studies for all trainees. | ST | X | X |  |  |  | TVET providers | NAQAA | TVET providers YEP
Operational objective 2.2 | Operational objective 2.2 Upgrade and diversify the range of ICT skills development programmes
1.2.1 | 1.2.1 Strengthen basic ICT skills training courses across education providersOn the following themes: - Office suites, including word processor, spreadsheet and presentation programme, and document editing - Basic Internet web search. | ST | X | X |  |  |  | Public and private TVET providersUniversities and colleges across all sectors | NAQAA | Sector association
2.2.2 | 2.2.2 Develop short-term specialized courses for technical and vocation training programmesOn the following themes: - Web content development - Hardware, mobile phones repair and deep repair - ICT user support. | ST | X | X |  |  |  | Public and private TVET providers | NAQAA | Sector association Foreign partners YEP
2.2.3 | 2.2.3 Develop and update quality technical and vocation training programmes at certificate and diploma levels on specialized topics- Software and multimedia development - Applications development and testing, including new courses on voice-based services, IoT and drones - Database management and data analytics. | MT |  | X | X | X |  | Public and private TVET providers | NAQAA | Sector associations Foreign partnersYEP
2.2.4 | 2.2.4 Upgrade quality of diploma delivered by the University of The Gambia (UTG) on: - General computer sciences - Upgrade IT equipment. | MT |  | X | X | X |  | UTG | NAQAA | Sector associations Foreign partners YEP
Operational objective 2.3 | Operational objective 2.3 Improve TVET capacities to deliver quality education in line with ICT sector requirements
2.3.1 | 2.3.1 Build technical teaching capacities of TVET and university staff Provide professional development activities for teachers in updated content, delivery techniques and managing on- and off-the-job training: - Incubator management, accelerator programmes, monitoring and evaluation frameworks - Building public-private partnerships to develop a project- IT project management. | MT |  | X | X |  |  | Public and private TVET providersUTG | ICT education providers’ working groups | Foreign partners
2.3.2 | 2.3.2 Establish a dedicated ICT research centre at UTG focusing on frugal innovation (‘Jugaad’) in ICTThe main focus will be to improve the use and access to new technology in rural areas and develop new ICT-enabled services. Train staff on frugal innovation concepts and develop partnerships with other ICT TVET that are part of the ‘Jugaad’ Innovation. | MT |  |  | X | X |  | UTG | ICT education providers’ working group | Foreign partners
2.3.3 | 2.3.3 Support TVET in building formal linkages with private sector Organize pitching events so trainees can showcase their products and look for potential partners or employers. | ST | X |  |  |  |  | Public and private TVET providersUTG | ITAG | Public and private TVET providersUTG
2.3.4 | 2.3.4 Develop ICT support student placement programmes for TVET Institutions graduating ICT professionals through apprenticeship and internship need to increase graduates’ prospects and the matching of industry needs with skills. - Develop student placement at UTG - Formalize internship and apprenticeship positions with private companies. | ST | X |  |  |  |  | TraineesPrivate companies | NAQAA | ITAG Public and private TVET providers UTG YEP
2.3.5 | 2.3.5 Create academic exchange Create programme for academic exchange with tech universities. | LT |  |  |  | X | X | Teachers | NAQAA | Public and private TVET providers UTG
3. | 3. Improve MSME productive capacities and market linkages
Operational objective 3.1 | Operational objective 3.1 Design and implement a digitization strategy for public agencies
3.1.1 | 3.1.1 Need assessment of ICT services and products in public services and evaluation of local ICT providersCarry out a need assessment for ICT equipment, services and training throughout the entire public sector. Identify current existing capacities among Gambian companies to carry out the public sector’s digitalization plan. | ST | X |  |  |  |  | Microwork initiative | Consultant | ITAGTech hub
3.1.2 | 3.1.2 Design digitization strategy for public agenciesOrganize a public-private roundtable to design the strategy and plan of action. | ST | X |  |  |  |  | Microwork initiative | MOICI | PURA ITAG Tech hub TGSB
3.1.3 | 3.1.3 Develop an ICT consortium to carry out the digitization plan of action and set up a microwork initiative Develop a consortium of selected companies to carry out the digitization plan and assist on the required policy review. | ST |  | X | X | X |  | Microwork initiative | ITAG | Tech hub Joko Labs
Operational objective 3.2 | Operational objective 3.2 Foster innovation and synergies among entrepreneurs and attract investment
3.2.1 | 3.2.1 Create a tech hubEstablish a shared space for ICT start-ups to enable dialogue and exchanges among local ICT firms. The tech hub should provide basic services, including: - Flexible leasing options that involve minimal commitment - High-speed Internet and business centre services.T his will foster collaboration between young developers and allow shared costs for R&D and personnel training. Potentially, micro and small companies will start collaborating to jointly market their services. | ST | X | X |  |  |  | Young entrepreneurs in ICT | ITAG | Tech labs Give1 Project Joko Labs ISPs GSM operators UTG MOICI YEP
3.2.2 | 3.2.2 Develop a tech parkSet up special infrastructure for FDI in ICT by creating and promoting a tech park. This will combine physical and legislative/regulatory infrastructure such as a special economic zone or export processing zone that would grant companies tax-free treatment on their imports (including hardware), exports and income, and preferential access to, and price treatment by, utilities and other services (e.g. telecoms and constant access to electricity). This should include a benchmarking analysis of previous attempts to create such structures in other Western African countries. | LT |  |  |  | X | X | MSMES in ICT-related services | GIEPA | PURA ITAG MOICI UNDP Gambia Public Procurement Authority
Operational objective 3.3 | Operational objective 3.3 Facilitate cross-sector synergies developing new ICT-enabled services and products
3.3.1 | 3.3.1 Organize regular hackathons to foster innovation and partnerships a) The hackathon should focus on particular immediate public and private sector needs to develop new products and services.Application development: - Education (availability of courses and content on cloud-based platforms) - Applications development to facilitate communication and logistics in agriculture and tourism.Hardware: - Maintenance, repair and deep repair.Multimedia content development for all sectors (especially tourism): - Web marketing in tourism.Database management:- In line with digitization for public sector (monitoring, administrative processes and taxes collection, etc.) - Trade facilitation (customs procedures). b) The new products and services developed would be a basis to facilitate linkages and create business partnerships between large established companies and young entrepreneurs to finance the development of ICT pilot projects. | ST | X | X | X |  |  | MSMES in ICT-related services Public agencies | ITAG | Tech hub YEP
3.3.2 | 3.3.2 Develop e-learning solutions for training institutions Develop e-learning, mobile learning or micro-learning solutions for TVET to improve access of youth in rural areas or complement existing courses. | ST | X | X | X |  |  | TVETs in other sectors | NAQAA | ITAG TVETs Tech hub ICT companies YEP
3.3.3 | 3.3.3 Organize ICT demo days Develop and implement local ICT diffusion programmes targeting local market segments to develop linkages, especially government, including local municipalities (particularly education and health) and business sectors such as financial services, tourism, accounting and auditing. | MT |  | X | X | X |  | MSMES in ICT-related services Young entrepreneurs in ICT | ITAG | GCCI American Chamber of Commerce Youth Entrepreneurs Association
Operational objective 3.4 | Operational objective 3.4 Improve the quality and suitability of digital skills across sectors
3.4.1 | 3.4.1 On-the-job training programme for non-ICT techniciansConduct specialized on-the-job training using blended learning (e-learning courses and face-to-face training workshops at the workplace) to facilitate the digital transformation of the sectors and uptake of new technologies such as sector-specific software, especially in the following areas:- Web and multimedia content management and publishing (in line with 2.2.2)- 3D modelling software in construction. | ST |  | X | X | X |  | MSMES in ICT-related services Young entrepreneurs in ICT | NAQAA | Working group of ICT education providers
3.4.2 | 3.4.2 On-the-job training programme for ICT techniciansConduct specialized on-the-job training using blended learning (e-learning courses and face-to-face training workshops at the workplace) to update and upgrade qualifications and competency level of employees in order to improve the quality of products and methodologies, especially in the following areas:- Broadcast technicians- Database specialists and systems administrators- Applications development and testing technicians. | ST |  | X | X | X |  | MSMES in ICT-related services Young entrepreneurs in ICT | NAQAA | Working group of ICT education providers
3.4.3 | 3.4.3 Incentives for ICT professionals Provide scholarships for advanced online courses to assist ICT professionals to continue their professional self-development plans. | MT |  |  | X | X |  | MSMES in ICT-related services Young entrepreneurs in ICT | ITAG | ICT education providers’ working group
Operational objective 3.5 | Operational objective 3.5 Develop partnerships with ICT multinationals targeting West Africa
3.5.1 | 3.5.1 Partnerships with international ICT companiesFacilitate business relationships for Gambian companies to become MNE-certified implementing partners for international ICT companies operating in Africa. Gambian companies would be trained and qualified to become implementing partners of renowned ICT companies in the subregion. | MT |  |  | X | X | X | Medium-size in ICT-related services | GIEPA | MOICI ITAG
4. | 4. Foster e-entrepreneurship and business growth in the ICT sector
Operational objective 4.1 | Operational objective 4.1 Foster the business growth of micro and small ICT companies
4.1.1 | 4.1.1 Build capacities of ICT incubators to foster ICT-entrepreneurship· Build the capacity of the Startup Incubator Gambia to link with other incubators in other countries· Develop an entrepreneurship guide. | ST | X | X | X |  |  | Young entrepreneurs in ICT | Startup Incubator | Tech hub YEP
4.1.2 | 4.1.2 IT start-up campaign to build linkages with the diasporaOrganize an IT start-up in the new Gambian campaign to facilitate linkages between members of the Gambian diaspora and local IT companies: - The campaign could facilitate school sponsoring - Investment and guidance - Equipment acquisition abroad - Outsourcing. | ST | X | X | X |  |  | Young entrepreneurs in ICT | ITAG | Tech hubStart-up Incubator
4.1.3 | 4.1.3 Develop an ICT-specific entrepreneurship and business growth support programme The programme will focus on providing market opportunities to existing entrepreneurs, improving their business skills, participating in a pitching competition to attract investors (Youth Entrepreneurship Summit) and business coaching. The programme will be supported by an entrepreneurship e-learning portal. | MT |  |  | X | X | X | Young entrepreneurs in ICT | GIEPA | ICT education providers’ working groupTech hub YEP
Operational objective 4.2 | Operational objective 4.2 Foster the development of ICT-enabled services in rural areas
4.2.1 | 4.2.1 Build the ICT capacities of youth centres in rural districts· Provide Internet access at cheap prices· Provide IT equipment (computers, webcams and routers, etc.) ·Organize online training sessions and entrepreneurship sensitization. | ST | X | X | X |  |  | Youth in rural areas | NYC | Youth centres in rural areas YEP
Operational objective 4.3 | Operational objective 4.3 Develop innovative financial products meeting market needs
4.3.1 | 4.3.1 Financial products for ICT businesses Promote the development and availability of financial products for ICT companies, avoiding the need for collateral other than contracts. | ST |  | X | X |  |  | MSMES in ICT-related services Young entrepreneurs in ICT | GIEPA | ITAG