## Sheet1
| Activities | Priority ST=Short term MT=Medium term LT=Long term | Starting period |  |  |  | Beneficiaries | Leading institutions | Implementing partners | Implementation progress | Implementation progress rate | Comments
|  |  | 2018 | 2019 | 2020 | 2021 |  |  |  | Implementation progress
1 | 1. Develop and reinforce youth entrepreneurship in nuts and agroprocessing | [11 empty] | Completed
Operational objective 1.1 | Operational objective 1.1 Encourage youth entrepreneurs in agribusiness sector | [11 empty] | under completion
1.1.1 | 1.1.1 Promote agropreneurship among youth - Develop sensitization campaign towards young farmers about agro-entrepreneurship to increase potential income and agro-food processing. Inform community leaders and the elderly about the benefits to engage youth in farming to facilitate the access to land and provide technical support. - Use radiobroadcasts, social media, text messaging and workshops. - Radio spots and workshops animated by traditional communicators and use of images recommended to communicate in the rural area (especially with illiterate youth). | ST | X | X | X | X | Young farmers | ASPA CAG NACOFAG | MOTIE GIEPA NEDI ASPA CAG YEP |  |  |  | To be programmed | 0.25
1.1.2 | 1.1.2 Develop an agropreneurship support programme for youth in farming and nursery a- Identify and engage pioneer groups of smallholder farmers willing and able to access more remunerative markets (abroad and locally). b-Identify, assess and profile, engage and cluster youths among selected groundnut and cashew farming communities willing and able to develop new income-generating activities (i.e. backyard poultry farming for birds and eggs) and improve household food security and nutrition. c- Organize a study tour to Sedima in Senegal to visit an experienced poultry agribusiness. | MT | X | X |  |  | Youth in rural areas involved in farming | ASPA CAG | ASPA CAG GSI NACOFAG CPMS YEP |  |  |  |  | 0.5
1.1.3 | 1.1.3 Develop an agropreneurship support programme for youth in agroprocessing a- Identify and engage pioneer youth groups willing and able to engage in primary agroprocessing. b- Provide customized training on processing techniques, food safety and packaging, oil extraction, food technology, including cooking oil technology, and quality management. | ST | X |  |  |  | Young agropreneurs | ASPA CAG GHE | ASPA NACOFAC GHE YEP |  |  |  |  | 0.75
Operational objective 1.2 | Operational objective 1.2 Provide financial support to youth entrepreneurs | [12 empty] | 1
1.2.1 | 1.2.1 Develop funding mechanism for young agropreneurs - Provide financial support to 1) youth involved in priority sectors and 2) to those who participated in the agropreneurship training programme by developing access to low interest rates in commercial banks and microfinance institutions, and a mini-grant scheme with social collateral to ensure their integration in the work market by providing financial support through a grant. - Develop and disseminate clear terms and conditions for accessing funds for those grants. | ST | X |  |  |  | Trained youth in agropreneurship programme | NACU | MOTIE NACCUG YEP
1.2.2 | 1.2.2 Build capacities in basic financial management of young agropreneurs Encourage youth participation in financial management trainings in order for them to be able to manage basic bookkeeping, financial planning and apply for loans. Training has to be delivered in local languages. | MT |  | X | X |  | Young entrepreneurs | NACU | NACU GSI YEP
2 | 2 Reinforce,the,production and processing capabilities
Operational objective 2.1 | Operational objective 2.1 Improve MSME productive capacities
2.1.1 | 2.1.1 Improve access to quality seeds and fertilizers - Develop access to a better variety of seeds and raise awareness on seeds quality issues through training and farmers field schools. - Carry out training of trainer programme on seed multiplication and selection, and plant propagation techniques. | ST | X | X |  |  | Producer | MoA NARI | ASPA Gambia College
2.1.2 | 2.1.2 Improve production and good farming practices - Provide training on good agricultural practices to farmers and monitoring - Disseminate existing manuals (in local languages or through oral classes) on good production techniques and intercropping to farmers’ associations and local communities. - Conduct regular monitoring of farmer associations’ use of GAP. Improve efficiency and enhance product quality, including aflatoxin reduction. | ST | X | X |  |  | Traders, operators and industrials | MoA | ASPA TGSB FSQA TGQA GSI NATC Future in Salikenni
2.1.3 | 2.1.3 Modernize farming system, especially in terms of irrigation and water management Pilot one or two modernized farming systems in rural districts to demonstrate good practices with the support of extension officers. | MT |  | X | X | X | Entire value chain | MoA | MoA Dept. of Community Development Sector associations
2.1.4 | 2.1.4 Improve post-harvest handling and storage management - Develop adequate storage facilities by providing training on post-harvest handling of groundnut to ensure compliance with standards and storage management training. - Pilot a storage-based credit facilitation mechanism in collaboration with commercial banks. - Roll out the pilot on the basis of results. | ST/MT | X | X | X |  | Farmers and cooperatives, traders, operators and industrials | MoA | DOA (KABA TLA SINCHU ALAGI) FSQA TGSB TGQA
2.1.5 | 2.1.5 Support the development of small-scale storage for nuts and cereals In the light of 2.1.3, provide and build up small-scale storage for nuts and cereals and processing facilities. | ST | X | X |  |  | Farmers and CPMS | MoA | DOA ASPA NACOFAC NAWFA CA National platform
Operational objective 2.2 | Operational objective 2.2 Improve and modernize agroprocessing
2.2.1 | 2.2.1 Disseminate new primary processing technologies for nuts and cereals, - Procure, deploy, transfer and showcase appropriate processing technologies and equipment aiming at strengthening productive capacities of local MSMEs involved in groundnut, cereals and cashew processing. - Waste used as biomass briquettes made from groundnut shells to be deployed at village level. | ST/MT | X | X |  |  | Farmers and CPMS Two pilot CPMS/demonstration centres to be fully equipped and supported by 2018 |  | DOAASP NAWFA Private institutions KABA TLA SINCHU ALAGI YEP
2.2.2 | 2.2.2 Develop small scale processing of groundnuts Develop small- and medium-scale processing units in order to improve food security and develop the national industrial base and increase the value of exports. | LT |  |  | X | X | Farmers and CPMS | Regions equipped | DOA GGC Processors’ associations NAFP
2.2.3 | 2.2.3 Develop secondary processing Secondary processing of cashew and groundnut butter-roasted snacks and peanut confections - Expand the range of cashew or groundnut, which can be roasted or processed into innovative convenience foods. - Improve knowledge of market requirements in terms of type of products, prices and quality. - Develop new ready-to-eat food for local retailers and institutional buyers.Secondary processing peanut and cashew oil Develop new quality oil for food market and local cuisine. | ST/MT | X | X | X |  | Small-scale processors | MoA (Food Technology Unit) | DOA GGC Processors’ associations NAFP GTTI
2.2.4 | 2.2.4 Modernize processing and packaging equipment - Develop or provide small-scale machinery for detoxification machinery. - Develop prototype machinery to separate bad quality nuts from good ones and insure proper maintenance. - Improve the packaging of established products to fulfil national retailers’ and exporters’ requirements. | ST/MT | X | X | X |  | Industrials and small-scale processors | NARI | DOA GGC Processors associations NAFP GTTI
Operational objective 2.3 | Operational objective 2.3 Improve quality management and packaging
2.3.1 | 2.3.1 Conduct food safety and HACCP awareness training for cooperatives and SMEs - Raise awareness on quality issues through training and farmers field schools. - Conduct a) HACCP implementation course and b) HACCP Lead Auditor Course through training in addition to direct support to selected enterprises.Assist selected exporters to become certified (ISO and HACCP, etc.). - Outreach initiatives and training aimed at reducing aflatoxin levels and improving food quality. | ST | X | X |  |  | Farmers organizations Cooperatives, Primary society of the village | FSQA TGSB | TGQA ASPA NAWFA CAG NACOFAG YEP
2.3.2 | 2.3.2 Strengthen lab capacities and testing facilities - Support lab staff training and purchase of testing equipment to improve pest and disease monitoring in line with nuts (cashew and groundnuts) standards. - Develop skills in laboratory testing and analysis for biological, chemical, heavy metal and physical food hazards. | MT |  | X |  |  | Non-exporting enterprises and exporters | NARI | TGSB FSQA GIEPA UTG
2.3.3 | 2.3.3 Sensitize collectors, transporters and exporters about quality related requirements, process standards and the need to comply with SPS and TBT requirements Carry out training of trainers on quality issues. Develop a handbook on quality for youth entrepreneurs and short courses on quality enhancement, process improvement (basics of LEAN), 5S and quality culture. Carry out training of trainers (ToT) on quality issues and development of support services through local institutions. Sensitize collectors and transporters on handling procedures to ensure adequate quality management of product during transport, temporary storage and transit storage. | ST | X | X | X | X | Exporters | FSQA TGSB | TVETs Media
2.3.4 | 2.3.4 Develop codes of conduct for value chain actors involved in exports for standard compliance and quality Assist sector associations to develop codes of conduct to define good practices For cashew: to reduce incidences of mixing different types cashews coming from different geographical locations. For groundnuts: for quality and standardization. | MT |  | X | X |  | Sector stakeholders | CAG ASPA | FSQA TGSB
2.3.5 | 2.3.5 Improve packaging, labelling and coding of processed products Improve the packaging of established products to fulfil national retailers’ and exporters’ requirements. | ST | X |  |  |  | Sector stakeholders | GIEPA Food processors GCCI | FSQA TGSB Agribusiness
Operational objective 2.4 | Operational objective 2.4 Reinforce market linkages and cross sector synergies
2.4.1 | 2.4.1 Increase awareness of local and foreign market requirements of value chain stakeholders Identify and disseminate local buyers’ needs and local market requirements among targeted youth entrepreneurs and farmers. Use existing and innovative ways to provide exporters and cooperatives with reliable and up-to-date market information pertaining to prices, produce and inputs availability and sources; cashew and groundnut trends in international and domestic markets ; and updates on policy and regulations in the sector. Provide training to value chain stakeholders on how to best use market information for business development. | ST | X |  |  |  | Entire value chain | GIEPA | ASPA CAG Agribusiness
2.4.2 | 2.4.2 Strengthen support capacities of sector associations to facilitate sector development coordination and youth agropreneurship - Provide targeted training and specialized support to selected associations to improve their support and training services. - Ensure full support to youth agropreneurship programme by assisting young farmers to access land and inputs, provide incentive to participate in sector association’s decision-making process and access to management positions. - Encourage cooperation and collaboration to improve market access, diminish the importance of middlemen in business transactions and secure sustainable business relationships. | MT |  | X |  |  | Entire value chain | Sector associations | NACOFAG
2.4.3 | 2.4.3 Facilitate the imports of raw material for packaging and machinery and identification of sustainable practices Building packaging capacities requires the importation of specific material to kick-start the activities. Research has to be carried out to identify eco-friendly material and best practices. | ST | X | X | X |  | Agro and food processors | MOTIE | MOTIE Sector associations
2.4.4 | 2.4.4 Improve the presentation and packaging of agroprocessed food locally produced - Build capacities of processors and exporters with training on packaging and labelling, use of presentable packaging material and quality consistency. - Support the development of a packaging centre. | MT |  | X | X |  | Agro and food processors | MOTIE | GIEPA
2.4.5 | 2.4.5 Promote locally produced agroprocessed food and nuts in local markets and abroad - Carry out a marketing campaign in collaboration with GIEPA, GCCI, GTB and Gambia Hotel Association to promote Gambian nuts and processed foods to hotels, tourists and local markets. -Promote agritourism with visits to cashew farms to sensitize tourists about local production. - Encourage Gambian embassies to promote Gambian nuts and participate in international trade fairs. | MT |  | X | X |  | Agro and food processors | GIEPA | GCCI GTB Gambia Hotel Association Media YEP
2.4.6 | 2.4.6 Facilitate the integration of new ICT technologies in nuts and agroprocessing Develop linkages between sector associations in agriculture and new communication technologies to develop new services using mobile data. | MT |  | X | X |  | Young farmers, Agroprocessors, IT developers | MOICI Gambia College | Gambia College GSI ITAG YEP
3 | 3 Develop youth skills through vocational training and upgrade TVET capacities
Operational objective 3.1 | Operational objective 3.1 Improve the quality and relevance of the skills development programmes offered by education providers
3.1.1 | 3.1.1 Create a high-level skills development coordination group Support the development of inter-ministerial coordination arrangements for skills development for agriculture | ST | X |  |  |  | Value chain stakeholders TVET | MoA | MoHERST MOYS NAQAA NYC GIEPA GCCI NACOFAG Sector associations
3.1.2 | 3.1.2 Establish a skill development plan in nuts and agroprocessing Promote national development of skills standards, common curriculum, learning materials and teacher training programmes with the involvement of all TVET providers and sector associations. | ST | X |  |  |  | Value chain stakeholders TVET | NAQAA | TVET providers NACOFAG
3.1.3 | 3.1.3 Improve capacity building capacities of TVET institutions and service providers Develop and update technical and vocational training programmes on: - Primary and secondary food processing and food safety, - Quality management and on post-harvest handling, - Certificate for machine maintenance in farming and agroprocessing. Provide machinery and equipment to TVET: - Create a certificate in packaging technology and specification at GTTI. | MT |  | X | X |  | Agribusiness TVET institutions | NAQAA | GSI NATC GTTI YEP
3.1.4 | 3.1.4 Develop and update university diploma on agriculture - Develop bachelor’s degree, diploma and certificate in quality management. - Create a lab technician diploma in UTG. - Bachelor in agribusiness in collaboration with MDI. - Certificate on nursery development. - Certificate on food processing focusing on food engineering and oil processing. | MT |  |  | X | X | Agribusiness TVET institutions | NAQAA | UTG Gambia College FSQA RDI
3.1.5 | 3.1.5 Reinforce teaching capacities of TVET - Provide professional development activities for teachers in updated content, delivery techniques and managing on- and off-the-job training. - Develop mobile learning programmes for remote areas and train teachers to implement and monitor activities and results. | MT |  |  | X | X | Teachers and trainers in TVET | NAQAA | UTG Gambia College GSI NATC GTTI WASDA ATC MMAP RDI YEP
Operational objective 3.2 | Operational objective 3.2 Upgrade youth skill through technical and vocational training programmes
3.2.1 | 3.2.1 Develop skills of young farmers in agribusiness Provide short-term training in management and leadership for current farmers and long-term programme for youth who would like to be engaged in farm management. | ST | X |  |  |  | Youth involved in agribusiness sector | NYS | NYS GSI NATC WASDA ATC MMAP GYIN Gambia NACOFAG YEP
3.2.2 | 3.2.2 Develop skills of young farmers in nursery management Train youth in nursery management (linked to agropreneurship programmes 1.1.2). Efficient production techniques. Choice of crops according to appropriate agro-ecological zones. | ST | X |  |  |  | Youth involved in farming | GSI | GSI NACOFAG CAG ASPA NYC YEP
1.2.3 | 1.2.3 Develop skills of youth in rural areas in mechanical repair - Train youth in mechanical training in on-farm repairs and proper on-farm routine maintenance. - Provide training in mechanical skills related to motor mechanics, engine maintenance, implement and irrigation system maintenance. | ST-MT | X | X |  |  | Food processing operatives | GTTI | GTTI NEDI NYSS PIA DOA YEP
3.2.4 | 3.2.4 Develop skills of youth in food processing and packaging - Enhance on-the-job learning programmes in food processing, including internships, traineeships and apprenticeships with certification schemes. - Develop new ready-to-eat food for local retailers and institutional buyers. | ST-MT | X | X |  |  | Food processing operatives | NAQAA | Private companies in food processing NACOFAG DOA FTS YEP
3.2.5 | 3.2.5 Develop skills of youth in agro-marketing Train youth in marketing in agribusiness, including market research, pricing, branding, marketing channels and selling. - Bachelor programme on administration and finance. - Training in business planning and entrepreneurial skills. | MT |  | X | X |  | Youth involved in agribusiness sector | MDI | Gambia College MDI GYIN Gambia GYCC NEDI YEP