## Sheet1
| Activities | Priority 1=high 2=med 3=low | Starting period |  |  |  |  | Beneficiaries | Leading institutions | Implementing partners | Implementation progress | Implementation progress rate | Comments
|  |  | 2018 | 2019 | 2020 | 2021 | 2022 |  |  |  | Implementation progress
1 | Strategic objective 1. Foster the creation of diversified tourism products and services
Operational objective 1.1 | Operational objective 1.1 Improve and diversify community-based and cultural tourism services up-country
1.1.1 | 1.1.1. Develop sustainable and inclusive development strategy for new destinations upriver - Develop a strategy development plan for Janjanbureh (activity started in 2017 with YEP support) - Establish a public–private–youth partnership to develop the strategic plan | 1 | [5 empty] | Community in Janjanbureh | GTB, VDC Governor’s office | GTH INCAC ITTOG ASSERT YEP |  |  |  | completed | 0.25
1.1.2 | 1.1.2 Encourage the review and improvement of existing tourism products using the Ninki Nanka Trail initiative - Improve safety of the river excursion to Baboon Island, and boat standards - Develop artistic signboards in cultural places - Improve existing community visitors’ experience (Kunkilling Forest Park and Ninki Nanka Trail) - Rejuvenate the Stone Circle Museum | 2 | [5 empty] | Youth upriver | GTB | NCAC ITTOG ASSERT YEP |  |  |  | Under completion | 0.5
1.1.3 | 1.1.3 Support for the creation of a visitor centre in Janjanbureh Develop multi-function information centre managed by youth to provide information, tourism services and commercial outlets for local food and crafts | 1 | [5 empty] | Youth in Janjanbureh area | GTB Government office | NCAC MOTIE MoYC YEP |  |  |  | To be programmed | 0.75
1.1.4 | 1.1.4 Diversify and improve community-based tourism experience - Train youth in tattooing, beading, preparation of traditional food and community tours - Train local villagers in improving the design of crafts and develop weaving | 2 | [5 empty] | Youth in Janjanbureh area | GTB | NCAC GTH IITTOG Identified villages in Central River Region YEP |  |  |  |  | 1
1.1.5 | 1.1.5 Develop local cultural festivals - Rejuvenate cultural events such as Kankurang and develop new festivals to attract tourists - Train youth in event management | 2 | [5 empty] | Youth in Janjanbureh | NCAC | GTB YEP
Operational objective 1.2 | Operational objective 1.2 Develop new tourism services and products in coastal areas
1.2.1 | 1.2.1 Raise capacity to design educational and study programmes - Build capacity of Class B tour operators and training institutions to design and operate high -quality educational programmes, and work effectively with local community guides to deliver great CBT experiences | [6 empty] | Tour operators and training institutions | GTB | ITTOG ASSERT GTHI Tour operators
1.2.2 | 1.2.2 Support the creation of cultural and sport events managed by youth - Develop new events using sports, art, dance and culture - Organize the 1st movie festival - Organize a chef competition to promote local cuisine | 2 | [5 empty] | Young artists | GTB NCAC GHA | FSDC ITTOG ASSERT GTHI Chef Association
1.2.3 | 1.2.3 Improve the services of beach bars - Support the creation of a beach bar association to foster cooperation - Train staff and bar owners in food safety and quality - Create a business growth training and mentoring programme for future beach bar owners and employees - Create a competition during the high season to improve services standards, develop promotional activities and foster linkages with hotels | 3 | [5 empty] | Beach bars | GTB | ITTOG ASSERT FSQA GTH IT GSB
Operational objective 1.3 | Operational objective 1.3 Foster backward market linkages between tourism private sector suppliers, ICT and agriculture
1.3.1 | 1.3.1. Improve access of young agropreneurs and craftsman to local tourism market - Create a weekend market for locally processed food and crafts made by youth initiatives targeting seasonal tourists - Develop a brand and concept around the ‘good market’ providing a distinct experience to tourists | 1 | [5 empty] | Youth entrepreneurs | ASSERT | GTB GCCI GHA ITTOG AACE
1.3.2 | 1.3.2. Develop linkages between locally produced agroprocessed food and hospitality service providers - Identify high-potential products through field research and interviews - Set up a youth entrepreneur catalogue of processed food suppliers - Organize business-to-business events and prizes for best products, packaging and quality - Provide support to improve packaging, food safety, quality management, marketing and negotiation | 1 | [5 empty] | Youth entrepreneurs in agroprocessing and hotel chefs | ASSERT Gambia Hotel Association | FSQA GTTI GHE
1.3.3 | 1.3.3. Improve MSMEs’ access to online marketing services in the tourism sector - Link small and medium companies with young multimedia and web designers to develop online information and web marketing campaign - Digitalize marketing materials and develop use of social media to position the services(Activities linked to entrepreneurship programme 1.1) | 2 | [5 empty] | Youth entrepreneurs | ASSERT | Association of Category B Tour Operators Information ITAG
1.3.4 | 1.3.4 Develop innovative destination promotion strategy for new tourism services upriver, focusing on cultural, adventure and educational tourism - Create new marketing material and public–private partnership around the Ninki Nanka Trail initiative, focusing on free independent travellers and small group adventure operators - Participate in international tourism trade fair to promote new tourism services - Organize familiarization trips for travels agents of small group adventure tour operators and educational programmes - Develop river cruise familiarization trip for artists (writers, painters, poets and musicians) from the diaspora community and European youth social media influencers for creative exploration and development of artistic online promotional material and mentoring Gambian youth artists | 2 | [5 empty] | Stakeholders involved in providing tourism services upriver | GTB | ITTOG GTHI ASSERT Association of Category B Tour Operators YEP Foreign tour operators specialized in small group adventure and educational programme Ground agents
2 | Strategic objective 2. Reinforce youth skills through vocational training and TVET strengthening
Operational objective 2.1 | Operational objective 2.1 Improve the quality and relevance of educational programmes
2.1.1 | 2.1.1. Improve the training capacities and quality of the Gambia Hospitality Training Institute- Update curriculum (done with YEP support in 2017)- Develop new content manual for each level (started with YEP support in 2017) - Develop waste cycling plant and courses - Get TedQual accreditation as a mark of quality education in tourism - Equip the library with recent publications and access to specialized online resources - Develop partnership with foreign TVET for specific course and programme development, professor visits and student exchange | 1 | [5 empty] | GTHI | NAQAA MoT | Foreign partners GHA
2.1.2 | 2.1.2. Improve the training capacities of TVET to deliver short-term courses and mentoring in new destinations up-country- Receive UNWTO high-impact training for short courses (started with YEP support in 2017) - Develop training programme for remote locations | 1 | [5 empty] | Hospitality service providers | GTHI ITTOG | ASSERT Tour Guide Association
2.1.3 | 2.1.3. Improve the training capacities and quality of ITTOG - Review and improve curriculum and develop a new business model - Develop partnership with foreign TVET for specific course and programme development, professor visits and student exchange - Develop short-term courses using new mobile learning technologies to facilitate remote mentoring - Create a certificate for tour guides specialized in birdwatching, river flora and fauna | 2 | [5 empty] | ITTOG | NAQAA MoT | Foreign partners ASSERT
Operational objective 2.2 | Operational objective 2.2 Upskill youth involved in hospitality services through-high impact training programmes
2.2.1 | 2.2.1. Develop youth skills in hospitality services in new rural destinations - Develop a part-time training programme focusing on the needs of the youth groups in Janjanbureh to become waiters, housekeepers, cooks, guides, receptionist or managers | 1 | [5 empty] | Youth in Janjanbureh and new destinations up-country | GTHI | Local government Hospitality service providers
2.2.2 | 2.2.2 Develop skills of youth in tour guiding, community-based tourism development and information services management - Train youth in tour guiding for birdwatching, cultural tours and adventures in collaboration with hotels and tour operators - Train youth in community-based tourism development -Train youth in basic reception skills in rural areas | 1 | [5 empty] | Youth in Janjanbureh and new destinations up-country | GTB | ITTOG GHA Local government NYC Local youth association
2.2.3 | 2.2.3 Develop youth skills in management of sport events, recreational activities and entertainment - Train youth to manage recreational activities in hotels such as: lifeguard, swimming instructor, fitness or dance instructor, tennis, volleyball and golf instructors, children’s recreational instructors, water sport or circus activities for children in collaboration with hotels and tour operators - Train youth to create and manage cultural or sport events | 2 | [5 empty] | Young athletes | GTB ASSERT NYC | GHA ITTOG MOYS NYC Sports federations ITTOG Fajara Skills Development Centre
2.2.4 | 2.2.4 Develop yout+K31+B24:N28+B23:N28+B22:N28+K31+B24:N28 | 2 | [5 empty] | Young designers | NAQAA NYC | TVET in creative industries Fajara Skills Development Centre
3 | Strategic objective 3. Develop and reinforce youth entrepreneurship in the tourism sector
Operational objective 3.1 | Operational objective 3.1 Encourage youth entrepreneurs in the tourism sector
3.1.1 | 3.1.1. Promote entrepreneurship in tourism and creative industries in rural areas up-country - Develop a youth entrepreneurship support programme in tourism in rural areas up-country - Identify, assess, profile and engage youth groups in selected destinations in rural areas up-country supported by local communities | 1 | [5 empty] | Youth entrepreneurs in rural areas | GTB | ASSERT GTH INCAC IITTOG YEP
3.1.2 | 3.1.2. Reinforce the products and services offered by young entrepreneurs in coastal areas through mentoring programme Create a business growth training and mentoring programme for young entrepreneurs in the coastal areas | 2 | [5 empty] | Youth entrepreneurs in coastal areasClass B tour operators | GTB | ASSERT GTH IITTOG MDI Association Class B Tour Operators Startup Incubator
Operational objective 3.2 | Operational objective 3.2 Provide financial support to youth entrepreneurs in tourism
3.2.1 | 3.2.1. Provide financial support to young entrepreneurs in rural areas - Through mini-grants, assist youth who participated in the tourism training programme to purchase equipment to develop their services - Develop and disseminate clear terms and conditions for accessing mini-grant scheme | 1 | [5 empty] | Trained youth | GTB | NACCUG YEP
3.2.2 | 3.2.2. Build basic financial skills capacity of young entrepreneurs and small business owners in coastal areas Train young entrepreneurs and small businesses owners to participate in financial management training to develop their capacity to manage basic bookkeeping and financial planning and apply for loans. | 2 | [5 empty] | Young entrepreneurs | MDI | GIEPA Empretec trainers